AI SHOPPING FOR BUDGETING & MAKING INFORMED SHOPPING

7-Day Build Sprint

A phase-by-phase plan for a 10-person team, from environment setup to a demo-ready system. Every phase lists exactly what each of the 10 members owns.

| START Mon 21 Sep 2026 | DEMO-READY Sun 27 Sep 2026 | PHASES 5 | TEAM SIZE 10 |
| --- | --- | --- | --- |

PHASE 1

Foundation & Setup

Mon 21 Sep — Day 1

Definition of done: Repo and boards are live, DB schema and API contracts are agreed on paper, wireframes exist for every core screen, and the seed-data plan is scoped.

| Member | Role | Tasks |
| --- | --- | --- |
| Member 1 | Team Lead / Scrum Master | - Confirm final MVP feature cut with the group (core requirements + Daily Budget Split only) - Set up shared repo + task board (GitHub Projects / Trello) - Lock daily 15-min standup time for all 7 days - Assign the 10 roles below and confirm everyone agrees to their lane |
| Member 2 | Backend Lead — Auth & database | - Scaffold backend project (Node/Express or Python/FastAPI) - Design DB schema: users, budgets, transactions, preferences - Stand up dev database (Postgres/MongoDB) and connect to scaffold - Share schema with the team for sign-off before Phase 2 |
| Member 3 | Backend Dev — Budget logic | - Write budget-management spec: entry, update, remaining-balance calc - Define overspend-warning rule (trigger when purchase > remaining budget) - Draft pseudocode/flowchart for budget recalculation on each transaction |
| Member 4 | Backend Dev — Search & filtering | - Draft search API contract (endpoint, query params, response shape) - List required filter fields: price, colour, size, brand, store, shipping, location, availability - Agree on natural-language search approach (keyword parsing vs. simple NLP) |
| Member 5 | AI/Recommendation Dev — Recommender logic | - Draft rule-based recommendation spec: score by budget fit, category match, distance - Define recommender input/output schema (shared with Member 4) |
| Member 6 | AI/Recommendation Dev — True cost & Budget Split | - Draft true-cost formula (base price + shipping + fees) - Draft Daily Budget Split algorithm (remaining allowance ÷ days to next payout) |
| Member 7 | Frontend Lead — UI architecture | - Scaffold frontend project (React) with routing skeleton - Pick colour palette & type scale; set up base design tokens - Wireframe all core screens: auth, budget dashboard, search, results, comparison |
| Member 8 | Frontend Dev — Auth & budget screens | - Build static register/login screen UI from wireframes - Build static budget-entry screen UI |
| Member 9 | Data / Frontend Dev — Seed data owner | - Build seed product dataset: 30–50 items with price, store, category, location, shipping fee - Save as JSON/CSV; confirm fields match Member 4's filter list |
| Member 10 | QA / Docs — Testing & documentation | - Turn the risk register (deck slide 21) into a running test checklist - Set up shared doc for meeting notes, decisions and blockers |

PHASE 2

Core Backend Build

Tue 22 – Wed 23 Sep — Days 2–3

Definition of done: Auth, budget CRUD and product search/filter endpoints work and are testable in isolation; frontend has real components and screens wired to whatever is ready.

| Member | Role | Tasks |
| --- | --- | --- |
| Member 1 | Team Lead | - Run daily standups; unblock dependencies between backend/frontend pairs - Track progress against the board; flag scope creep early |
| Member 2 | Backend Lead | - Implement register / login / logout (JWT or session-based) - Implement profile & preferences management endpoints |
| Member 3 | Backend Dev | - Implement budget entry/update endpoint - Implement remaining-budget calculation + overspend warning - Write unit tests for budget-calc edge cases (zero, negative, exact match) |
| Member 4 | Backend Dev | - Implement keyword + natural-language search endpoint - Implement multi-criteria filter endpoint against seed data |
| Member 5 | AI Dev | - Implement first working recommender pass using seed data (budget + category filter/sort) |
| Member 6 | AI Dev | - Implement true-cost calculator function - Start Daily Budget Split endpoint |
| Member 7 | Frontend Lead | - Build reusable component library: buttons, inputs, cards, nav - Wire up app routing between all screens |
| Member 8 | Frontend Dev | - Wire auth screens to Member 2's live API - Build budget-dashboard screen (static — wiring starts Phase 3) |
| Member 9 | Data / Frontend Dev | - Load seed dataset into the dev DB / mock API - Start building product search-results screen UI |
| Member 10 | QA / Docs | - Test auth + budget endpoints as they land; log bugs on the board - Keep meeting notes and blocker log current |

PHASE 3

AI Layer, Frontend Wiring & Standout Feature

Thu 24 – Fri 25 Sep — Days 4–5

Definition of done: Recommendations are live end-to-end, the budget dashboard is fully wired, and Daily Budget Split works from backend to screen.

| Member | Role | Tasks |
| --- | --- | --- |
| Member 1 | Team Lead | - Check integration points between AI, backend and frontend daily |
| Member 2 | Backend Lead | - Fix auth/session bugs surfaced by frontend integration - Support token handling across all endpoints |
| Member 3 | Backend Dev | - Wire budget dashboard endpoint to remaining-budget + warning display - Integrate Daily Budget Split output into the budget response payload |
| Member 4 | Backend Dev | - Handle search/filter edge cases: no results, invalid filter combos - Add pagination to search results |
| Member 5 | AI Dev | - Finish recommender: integrate true-cost + budget-fit scoring - Test recommendation output against 3–4 sample budgets/scenarios |
| Member 6 | AI Dev | - Finish Daily Budget Split feature end-to-end - Hand off response format to Member 8 for UI display |
| Member 7 | Frontend Lead | - Build recommendation-results screen: cards, sort, filter controls - Confirm responsive layout across all screens so far |
| Member 8 | Frontend Dev | - Wire budget dashboard screen to Member 3's live API - Build the Daily Budget Split display component |
| Member 9 | Data / Frontend Dev | - Build cross-source product comparison view - Wire search-results screen to Member 4's live API |
| Member 10 | QA / Docs | - Test recommendation engine + search against the risk-register checklist - Log and prioritise bugs; start drafting the demo script |

PHASE 4

Integration & Full System Test

Sat 26 Sep — Day 6

Definition of done: The full flow works end-to-end — register, set budget, search, get a recommendation, see true cost — with no blocking bugs left open.

| Member | Role | Tasks |
| --- | --- | --- |
| Member 1 | Team Lead | - Run a full-team integration session; resolve merge conflicts - Confirm the demo flow order with the group |
| Member 2 | Backend Lead | - Fix remaining auth/session integration bugs |
| Member 3 | Backend Dev | - Fix budget-calc edge cases found during testing |
| Member 4 | Backend Dev | - Fix search/filter integration bugs; verify combos work with the recommender |
| Member 5 | AI Dev | - Tune recommendation scoring based on integration-test results |
| Member 6 | AI Dev | - Validate true-cost & Daily Budget Split numbers across test scenarios |
| Member 7 | Frontend Lead | - Full UI polish pass: consistent spacing, colour, type across every screen |
| Member 8 | Frontend Dev | - Fix frontend bugs found in integration - Cross-browser / device check |
| Member 9 | Data / Frontend Dev | - Fix data bugs (missing fields, bad seed rows) - Finalise comparison and search-results UI |
| Member 10 | QA / Docs | - Run full regression against the risk-register checklist - Log the final bug list and assign each item an owner |

PHASE 5

Polish, Documentation & Demo Prep

Sun 27 Sep — Day 7

Definition of done: Every open bug from Day 6 is closed or accepted, the deck's Timeline and References slides are complete, and the team has rehearsed the demo at least once.

| Member | Role | Tasks |
| --- | --- | --- |
| Member 1 | Team Lead | - Run a full dry-run of the demo with the whole team - Finalise speaking order and submit final project files |
| Member 2 | Backend Lead | - Close remaining auth/DB bugs from Day 6's list |
| Member 3 | Backend Dev | - Close remaining budget-logic bugs |
| Member 4 | Backend Dev | - Close remaining search/filter bugs |
| Member 5 | AI Dev | - Close remaining recommendation bugs |
| Member 6 | AI Dev | - Close remaining true-cost / Budget Split bugs |
| Member 7 | Frontend Lead | - Final visual QA pass on every screen - Record a backup screen-capture of the demo in case live demo fails |
| Member 8 | Frontend Dev | - Final polish on auth & budget-dashboard screens |
| Member 9 | Data / Frontend Dev | - Final polish on search, filter & comparison screens |
| Member 10 | QA / Docs | - Finalise test documentation and the README/user guide - Complete the deck's References slide (Harvard, min. 10 sources) and fill in the Timeline slide |

Notes

Roles are placeholders — swap “Member 1–10” for real names once assignments are confirmed. Keep live status on a shared task board (set up in Phase 1 by Member 1); this document is the reference plan, not the live tracker.

The plan scopes to the MVP plus one standout feature (Daily Budget Split). Swap Member 5/6's tasks if the group prioritises a different standout feature.